## Slide 1
Better Targeted Super Concessions NOTE: Pending legislation |  |  |  |  |  |  |  |  |  |  |  | 
Payday Super NOTE: Pending legislation |  |  |  |  |  |  |  |  |  |  |  | 
Super Guarantee rate rise |  |  |  |  |  |  |  |  |  |  |  | 
Changes impacting the superannuation industry
Design
Build
Test
Onboarding
A
ATO activity
F
Industry (fund) activity
E
Employer/Employee activity
JUN
DEC
2023
SEP
OCT
NOV
JUL
AUG
FEB
2024
MAR
APR
MAY
JAN
As at May 2023
A
ATO to design and build functionality to administer the reduction of tax concessions available to individuals whose total super balances exceed $3million at the end of the financial year. May 2023 – July 2026
ATO to build and implement systems to enable additional fund reporting and individual tax determinations. May 2023 - July 2026
ATO consulting with stakeholders on the design of these changes, with the final design to be considered as part of the 2024–25 Budget.
Anticipated start date 1 July 2026
A
ATO test and deploy new 11% SG rate
A
E
11% SG rate applies from 1 July 2023
E
July 2026 (anticipated start date) Employers commence paying super at the same time as salary and wages
July 2025 (anticipated start date) Funds commence reporting additional data to the ATO
F

## Slide 2
Deliverable | Change | Version
Better Targeted Super Concessions | Added as announced in the May 2023 Federal Budget | May 2023
Payday Super | Added as announced in the May 2023 Federal Budget | May 2023
Your Future, Your Super | Removed as project delivery is complete | May 2023
KiwiSaver | Removed as project delivery is complete | March 2023
Downsizer Contributions | Removed as project delivery is complete | March 2023
Your Future, Your Super | Updated to reflect next phase of project delivery | November 2022
KiwiSaver | Updated to reflect next phase of project delivery | November 2022
Downsizer Contributions | Added as announced in the October 2022 Federal Budget | November 2022
KiwiSaver | Updated to reflect changed delivery timelines | July 2022
Your Future, Your Super | Updated to reflect changed delivery timelines | July 2022
Account Matching Service | Removed as project currently on hold | July 2022
SMSF Legacy Retirement Product Conversions | Removed as legislation has not progressed at this stage | July 2022
Recontribution of COVID-19 early release of super contributions | Removed as project delivery is complete | July 2022
Change Control
* Change Control is limited to the past 12 months